## 1. Overview
PROJECT NEXUS — PRODUCT COMPLETION PLAN (Release 1)
Source: SRS Nexus E-Commerce & Auction v1.0 (04/06/2026, HauNK) · Prepared by: Tuan Nghiem · Date: 22/09/2026
A. CAPACITY MATH — WHY 6 MONTHS ISN'T ENOUGH
Metric | Value | Unit |  | Calculation / Notes
Total SRS v1.0 scope (full) | 816 | dev-day |  | All of SRS sections 3, 4, 5 at production depth — EXCLUDES tech-stack training
• SRS features | 609 | dev-day |  | Sheet “2. Backlog” — total of the Estimate column, minus the 3 training tasks
• Tech-stack training (sprint S0) | 44 | dev-day |  | Sheet “2. Backlog” — F01.0a/b/c, not part of SRS scope
• Deferred to R1.1 / R2 | 207 | dev-day |  | Sheet “6. Deferred” — each item has a reason
Release 1 scope (SRS features + training) | 653 | dev-day |  | Actual scope the team must deliver over 17 sprints (S0–S16)
Proposed team | 8 | people |  | 1 PO/PM, 1 Tech Lead, 4 Backend, 1 Frontend, 1 QA (sheet 8)
Effective dev capacity | 5.5 | FTE |  | Tech Lead 50% + 4 Backend + 1 Frontend. PO/PM and QA aren't counted in dev capacity
Output per FTE per sprint | 8 | dev-day |  | 10 working days x 80% (ceremonies, code review, support, bug fixes)
Dev capacity per sprint | 44 | dev-day |  | 5.5 FTE x 8 dev-day
Sprints needed for R1 scope | 14.8 | sprint |  | Not counting the inception sprint or the hardening sprint
If holding the 6-month target (10 effective sprints) | 8.2 | FTE |  | Dev FTE NEEDED to finish R1 scope in 10 effective sprints (after subtracting Christmas/Tet + training)
CONCLUSION | R1 scope needs 14.8 sprints of dev work. To finish in 10 effective sprints (6 months, after subtracting Christmas/Tet + training) requires 8.2 dev FTE, i.e. a team of about 11 (Option A). Keeping an 8-person team needs 17 sprints = 8.4 months.
B. THREE OPTIONS — DECISION NEEDED BEFORE 30/09/2026
Option | Team | Go-live | Duration | Pros / Cons
A. Hold the 6-month date - add headcount | 11 people (1 PM, 1 TL, 7 BE, 1 FE, 1 QA) | 16/04/2027 | 6.6 months | (+) Nearly hits the 6-month mark; keeps full scope (-) Cost rises about 37%; onboarding 3 new devs into a greenfield project (Brooks' law); hiring must close before 30/09/2026; should hire people who already know Java/Spring Boot to avoid extending the training sprint Scope: Full Must-scope (653 dev-day, including 44d tech-stack training)
B. Keep the 8-person team - extend the timeline (RECOMMENDED) | 8 people (1 PM, 1 TL, 4 BE, 1 FE, 1 QA) | 12/06/2027 | 8.4 months | (+) Lowest cost; small, stable team, low communication overhead (-) 2 months later than the original target Scope: Full Must-scope (653 dev-day, including 44d tech-stack training)
C. Hold the 6-month date - cut auction | 8 people | 30/04/2027 | 7.0 months | (+) Nearly hits the date, no added cost (-) Loses the product's key differentiator; auction is the whole reason Project Nexus exists Scope: E-commerce only (518 dev-day, including 44d tech-stack training). Auction moves to R2, Q4 2027
C. KEY ASSUMPTIONS (if any of these is wrong, the plan must be redone)
• ADR-002: use a MODULAR MONOLITH (bounded contexts + separate schemas + event bus) for 6 domains, with the Auction Service SPLIT OUT separately. 7 microservices with 5 devs is an anti-pattern; this assumption saves roughly 60 dev-day of platform and operational work.
• Frontend has NO custom design: admin and seller portal use a ready-made template (Ant Design Pro / Refine), the buyer web uses Tailwind with a component library. The 101 dev-day frontend estimate is only sufficient at this level.
• Only 1 payment gateway (Stripe) and 1 carrier (GHN) are integrated in R1. The adapter framework is ready to add more carriers later.
• PostgreSQL Full-Text Search is sufficient to meet the <= 800ms search SLA up to about 500,000 products. OpenSearch is deferred to R1.1.
• SRS v1.1 (adding System Context, Architecture, Component diagrams and a promotions spec) is completed before S3 = 20/11/2026.
• 1 dev-day is 1 EFFECTIVE working day (after subtracting 20% for ceremonies, support, review) — not 1 calendar day.
• The actual dev buffer is only 3.8% (Track B) to 11.5% (Track A) — LOW versus the 20-25% standard for a greenfield project. As a result: the target go-live is 12/06/2027, and the externally COMMITTED go-live is 26/06/2027 (adding 1 contingency sprint).

## 2. Backlog
Feature ID | Epic | Epic Name | Feature Name | SRS ref | Priority | Estimate (dev-day) | Track | Sprint | Dependencies | Definition of Done
F01.0a | E01 | Platform Foundation | Tech stack training - Backend: Java, Spring Boot (Tech Lead + Backend Track A) | - | Must | 20 | A | S0 | - | Complete the Java + Spring Boot training/hands-on course; build 1 sample CRUD service with unit tests and DB connectivity
F01.0b | E01 | Platform Foundation | Tech stack training - Backend: Java, Spring Boot (Backend Track B) | - | Must | 16 | B | S0 | - | Complete the same training/hands-on course as Track A
F01.0c | E01 | Platform Foundation | Tech stack training - Frontend: ReactJS, HTML, CSS | - | Must | 8 | FE | S0 | - | Build 1 sample page with components, state, API calls, responsive HTML/CSS
F01.1 | E01 | Platform Foundation | Finalize tech stack + ADRs + repository structure | 4.1 | Must | 3 | A | S1 | - | ADR-001..005 signed off by Tech Lead and PO
F01.2 | E01 | Platform Foundation | Service/module template (clean architecture, DDD, health checks, config) | 4.1 | Must | 5 | A | S1 | F01.1 | Scaffold a new module in under 1 hour
F01.5 | E01 | Platform Foundation | CI/CD: build, test, SAST, container scanning, rolling deploy | 5.7 | Must | 8 | A | S1 | F01.1 | Commit to STAGING in under 15 minutes, zero downtime
F01.3 | E01 | Platform Foundation | API Gateway: routing, rate limiting, JWT validation | 5.4 | Must | 5 | A | S2 | F01.2 | Requests through the gateway carry a trace-id
F01.4 | E01 | Platform Foundation | Event bus (Kafka) + schema registry + Outbox library | 2.8 | Must | 9 | A | S2 | F01.2 | Publish/consume 1 real event, at-least-once with dedup
F01.6 | E01 | Platform Foundation | DEV/STAGING environments on K8s + secret management | 4.3 | Must | 5 | A | S2 | F01.5 | No secrets remain in source code
F13.1 | E13 | Web Frontend (Buyer / Seller / Admin) | Design system + component library + responsive framework | - | Must | 12 | FE | S2–S3 | F01.3 | Storybook; 20 base components
F01.7 | E01 | Platform Foundation | Observability: OpenTelemetry, Prometheus, Grafana, centralized logging | 5.5 | Must | 4 | A | S3 | F01.6 | Trace spans gateway to service to DB; p95/p99 dashboard
F01.8 | E01 | Platform Foundation | Shared library: idempotency, correlation-id, error contract, OpenAPI generation | 4.2 | Must | 3 | A | S3 | F01.2 | OpenAPI spec generated from code and auto-published
F02.1 | E02 | User Service - Identity & Access | User CRUD + validation + soft delete + audit log | 3.1.1 | Must | 10 | A | S3 | F01.8 | 8 APIs with audit logging who / when / which field
F03.1 | E03 | Notification Service | Event log consumer + storage + list/detail API | 3.2.1 | Must | 9 | B | S3 | F01.4 | Every published event has a log record
F03.2 | E03 | Notification Service | Email channel + template engine + provider integration | 3.2.3 | Must | 6 | B | S3 | F03.1 | Can send 6 transactional templates
F14.1 | E14 | Quality & NFR Compliance | Test automation framework + API contract tests | 5.6 | Must | 10 | QA | S3–S4 | F01.5 | Contract tests run in CI and block merges
F02.3 | E02 | User Service - Identity & Access | OAuth2/JWT authentication + refresh token + session timeout | 5.4 | Must | 12 | A | S4 | F02.1 | Login <= 500ms; token expiry per configuration
F02.4 | E02 | User Service - Identity & Access | Account lockout after N failed attempts + password policy | 2.6 | Must | 4 | A | S4 | F02.3 | Locks out after MAX_LOGIN_ATTEMPTS = 5
F03.3 | E03 | Notification Service | Event-to-notification mapping rules | 3.2.3 | Must | 4 | B | S4 | F03.2 | Mapping table is configurable, not hardcoded
F03.8 | E03 | Notification Service | Message broker health check + pause/resume + events | 3.2.2 | Must | 3 | B | S4 | F01.4 | Broker down: core API still returns 200, notifications queue up
F10.1 | E10 | Fulfillment - Inventory / Warehouse | Inventory record by SKU x warehouse + derived available quantity | 3.6.1 | Must | 8 | B | S4 | F01.8 | available = total - reserved - unavailable
F13.2 | E13 | Web Frontend (Buyer / Seller / Admin) | Auth screens: sign up, sign in, forgot password, profile | - | Must | 8 | FE | S4 | F02.3 | Lighthouse accessibility >= 90
F02.5 | E02 | User Service - Identity & Access | Forgot password / reset via email token | 3.1.1 | Must | 5 | A | S5 | F02.3, F03.2 | Single-use token, expires in 15 minutes
F02.6 | E02 | User Service - Identity & Access | Change password | 3.1.1 | Must | 3 | A | S5 | F02.3 | Blocks reuse of the previous password
F02.7 | E02 | User Service - Identity & Access | Publish 8 user domain events | 2.8 | Must | 5 | A | S5 | F01.4 | Events appear in the Event Log Service
F04.1 | E04 | Catalog Service | Product CRUD + status + images (up to 5) + audit | 3.3.1 | Must | 10 | A | S5–S6 | F01.8 | DRAFT/ACTIVE/INACTIVE; blocks deletion once an order exists
F10.2 | E10 | Fulfillment - Inventory / Warehouse | Stock reservation - atomic, prevents overselling | 3.6.1 | Must | 12 | B | S5 | F10.1 | No overselling with 200 concurrent reservations
F10.4 | E10 | Fulfillment - Inventory / Warehouse | Inventory ledger (append-only, immutable) | 3.6.1 | Must | 4 | B | S5 | F10.1 | No UPDATE/DELETE on the ledger
F13.3 | E13 | Web Frontend (Buyer / Seller / Admin) | Buyer: homepage, category browsing, product list & detail | - | Must | 14 | FE | S5–S6 | F04.1 (search uses a contract mock) | LCP <= 2.5s
F04.2 | E04 | Catalog Service | Category CRUD + hierarchy tree up to 3 levels | 3.3.2 | Must | 6 | A | S6 | F04.1 | Blocks deleting a category that still has products
F04.3 | E04 | Catalog Service | Search + filter + sort + pagination (Postgres FTS) | 3.3.3 | Must | 8 | A | S6–S7 | F04.2 | Search <= 800ms with 100,000 products
F04.5 | E04 | Catalog Service | SKU / product variant model | 3.6.1 | Must | 3 | A | S6 | F04.1 | Inventory can reference SKUs
F07.1 | E07 | Auction - Session Management | Create auction session + validate seller / product / no duplicate active session | 3.5.1 | Must | 10 | B | S6–S7 | F04.1 | Blocks 2 active sessions for the same product
F10.3 | E10 | Fulfillment - Inventory / Warehouse | Reservation check + expiry job + stock release | 3.6.1 | Must | 7 | B | S6 | F10.2 | Reservation auto-releases after 30 minutes
F10.5 | E10 | Fulfillment - Inventory / Warehouse | Inventory change handling + event-driven update rules | 3.6.1 | Must | 5 | B | S6 | F10.4 | Paid → deduct stock; canceled/failed → release stock
F04.4 | E04 | Catalog Service | Publish catalog domain events | 2.8 | Must | 3 | A | S7 | F01.4 | 5 catalog events
F05.1 | E05 | Commerce - Cart, Checkout, Payment | Cart lifecycle: guest cart, merge on login, expiry job | 3.4.1 | Must | 12 | A | S7 | F04.1 | 1 active cart per user; expires after 7 days
F07.2 | E07 | Auction - Session Management | Auction session configuration (before start only) | 3.5.1 | Must | 5 | B | S7 | F07.1 | Configuration locks once the session is ACTIVE
F07.3 | E07 | Auction - Session Management | Session lifecycle scheduler: auto start / end + blocks invalid state | 3.5.1 | Must | 12 | B | S7–S8 | F07.1 | Start/end timing drift <= 5 seconds
F13.8 | E13 | Web Frontend (Buyer / Seller / Admin) | Admin console (lightweight): users, categories, orders, config, event log | - | Must | 6 | FE | S7 | F02.1 | Uses an admin template, no custom design
F05.2 | E05 | Commerce - Cart, Checkout, Payment | Add / edit / remove cart items + validation | 3.4.1 | Must | 8 | A | S8 | F05.1 | Add to cart <= 500ms
F05.3 | E05 | Commerce - Cart, Checkout, Payment | Cart pricing: subtotal, tax, discounts, estimated shipping | 3.4.1 | Must | 10 | A | S8–S9 | F05.2 | Matches 100% with the checkout price recalculation step
F07.4 | E07 | Auction - Session Management | Session cancellation: conditions, handling, events, consistency, audit | 3.5.1 | Must | 5 | B | S8 | F07.3 | After cancellation: blocks both bidding and settlement
F13.7 | E13 | Web Frontend (Buyer / Seller / Admin) | Seller portal (lightweight): products, inventory, auction session creation, order handling | - | Must | 8 | FE | S8–S9 | F04.1 | Web only, no mobile app
F05.4 | E05 | Commerce - Cart, Checkout, Payment | Cart validation before checkout | 3.4.1 | Must | 5 | A | S9 | F05.3 | Catches out-of-stock / price-changed / INACTIVE products
F05.5 | E05 | Commerce - Cart, Checkout, Payment | Checkout flow: address, method, price recalculation, timeout | 3.4.2 | Must | 14 | A | S9–S10 | F05.4, F10.2 | 15-minute timeout releases the reservation
F07.5 | E07 | Auction - Session Management | Admin force-cancel session | 3.5.1 | Must | 2 | B | S9 | F07.4 | Event records the admin who performed the action
F08.1 | E08 | Auction - Bidding | Place bid + validate active session / minimum increment / bidder eligibility | 3.5.2 | Must | 12 | B | S9–S10 | F07.3 | Bid placement <= 300ms
F13.4 | E13 | Web Frontend (Buyer / Seller / Admin) | Buyer: cart + checkout + payment | - | Must | 16 | FE | S9–S11 | F05.5 | Stripe Elements; never touches card data
F05.6 | E05 | Commerce - Cart, Checkout, Payment | Stripe integration - payment initiation | 3.4.2 | Must | 10 | A | S10 | F05.5 | E2E on sandbox; card number / CVV never stored
F08.2 | E08 | Auction - Bidding | Bid concurrency handling (Redis + optimistic locking) | 3.5.2, 5.1 | Must | 14 | B | S10 | F08.1 | No lost bids, no ordering errors at 3,000 bids/minute
F00.FE | E13 | Web Frontend (Buyer / Seller / Admin) | Frontend polish: accessibility, cross-browser | - | Must | 13 | FE | S11–S15 | - | Lighthouse accessibility >= 90 on 5 key pages
F05.7 | E05 | Commerce - Cart, Checkout, Payment | Payment confirmation webhook + idempotency window + retry | 3.4.2 | Must | 14 | A | S11 | F05.6 | Duplicate webhook does not create 2 orders; retries 3 times
F06.1 | E06 | Commerce - Order Management | Order creation + product/price snapshot + idempotency key | 3.4.3 | Must | 14 | A | S11–S12 | F05.7 | Order creation <= 1.5s; idempotent
F08.3 | E08 | Auction - Bidding | Bid history + display rules | 3.5.2 | Must | 6 | B | S11 | F08.1 | Masks bidder identity per the rules
F08.4 | E08 | Auction - Bidding | Outbid detection + event emission | 3.5.2 | Must | 4 | B | S11 | F08.2 | Outbid event reaches Notification <= 1s
F08.5 | E08 | Auction - Bidding | Anti-sniping: end-time extension + extension cap | 3.5.2 | Must | 5 | B | S11 | F08.2 | 5-minute extension, capped per configuration
F14.3 | E14 | Quality & NFR Compliance | Performance testing: 3,000 bids/minute, catalog 1,000 rps | 5.1 | Must | 8 | QA | S11–S12 | F08.2, F04.3 | Meets every SLA in SRS section 5.1
F06.2 | E06 | Commerce - Order Management | Order status state machine + blocks invalid transitions | 3.4.3 | Must | 10 | A | S12 | F06.1 | Blocks every invalid transition
F08.6 | E08 | Auction - Bidding | Realtime price push (WebSocket/SSE) | 5.1 | Must | 7 | B | S12 | F08.2 | 1,000 clients/session receive updates <= 1s
F09.1 | E09 | Auction - Settlement | Session end processing + session lock | 3.5.3 | Must | 5 | B | S12 | F07.3 | After ending: 100% of bids are rejected
F09.2 | E09 | Auction - Settlement | Determine winner + handle sessions with no bids | 3.5.3 | Must | 4 | B | S12 | F09.1 | At most 1 winner per session
F13.6 | E13 | Web Frontend (Buyer / Seller / Admin) | Auction: list, detail, realtime bidding UI, price history | - | Must | 16 | FE | S12–S14 | F08.3, F08.6 | Realtime update <= 1s
F06.3 | E06 | Commerce - Order Management | Order tracking + status history | 3.4.3 | Must | 6 | A | S13 | F06.2 | Displays the full timeline
F06.4 | E06 | Commerce - Order Management | Order history + filter by status / date | 3.4.3 | Must | 4 | A | S13 | F06.2 | Has an empty-state "No data" view
F09.3 | E09 | Auction - Settlement | Settlement event → Commerce creates the order (Auction never creates orders itself) | 3.5.3 | Must | 9 | B | S13 | F09.2, F06.1 | Saga: session settled → order gets created
F09.4 | E09 | Auction - Settlement | Payment deadline enforcement + timeout event + reputation penalty | 3.5.3 | Must | 9 | B | S13–S14 | F09.3, F12.2 | Past 24h fires a timeout event and deducts reputation points
F12.2 | E12 | User Reputation | Reputation score + trust level calculation | 3.1.2 | Must | 5 | A | S13 | F02.1 | Score recalculates on review or penalty
F12.3 | E12 | User Reputation | Enforce MIN_REPUTATION_TO_BID / TO_SELL rules | 3.1.2 | Must | 3 | A | S13 | F12.2, F07.1, F08.1 | Blocks bidding / session creation below threshold (toggled via FEATURE_REPUTATION_ENFORCEMENT)
F13.5 | E13 | Web Frontend (Buyer / Seller / Admin) | Buyer: order history + shipment tracking | - | Must | 8 | FE | S13–S14 | F06.3, F06.4 | -
F14.2 | E14 | Quality & NFR Compliance | E2E automation for critical flows | 5.6 | Must | 12 | QA | S13–S14 | F06.1, F06.5 | Covers: checkout, bidding, settlement, refunds
F06.5 | E06 | Commerce - Order Management | Order cancellation + refund flow + refund status tracking | 3.4.2 | Must | 10 | A | S14 | F06.2, F05.7 | Refund is idempotent and reconcilable
F09.5 | E09 | Auction - Settlement | Settlement completion + exactly-once handling | 3.5.3 | Must | 9 | B | S14 | F09.4 | Re-running settlement does not change the outcome
F10.6 | E10 | Fulfillment - Inventory / Warehouse | Stock reservation for auction sessions + settlement handling | 3.6.1 | Must | 6 | B | S14–S15 | F10.2, F09.5 | Session created → stock reserved; session failed → stock released
F11.1 | E11 | Fulfillment - Shipping & Logistics | Shipping orchestrator + shipment entity + internal status model | 3.6.2 | Must | 8 | A | S14 | F06.2 | Shipment is linked to the order and warehouse
F00.B | E14 | Quality & NFR Compliance | Integration hardening & bug fixing (Track B) | - | Must | 15 | B | S15 | - | Closes every Major defect in the auction flow
F06.6 | E06 | Commerce - Order Management | Admin order management + exception handling | 3.4.3 | Must | 5 | A | S15 | F06.2 | Admin can change status within allowed limits
F11.2 | E11 | Fulfillment - Shipping & Logistics | Carrier adapter framework | 3.6.2 | Must | 5 | A | S15 | F11.1 | Adding a new carrier requires no core changes
F11.3 | E11 | Fulfillment - Shipping & Logistics | GHN adapter: rate quote, waybill creation, tracking webhook | 3.6.2 | Must | 8 | A | S15 | F11.2 | E2E on GHN sandbox
F11.4 | E11 | Fulfillment - Shipping & Logistics | Carrier status mapping + idempotent updates + events | 3.6.2 | Must | 3 | A | S16 | F11.3 | Duplicate webhook does not change status
F11.5 | E11 | Fulfillment - Shipping & Logistics | Retry policy for carrier failures | 3.6.2 | Must | 2 | A | S16 | F11.3 | Carrier outage does not block order processing
F12.1 | E12 | User Reputation | Post-transaction review (once per party, no self-review) | 3.1.2 | Must | 6 | A | S16 | F06.2, F09.5 | Reviews only allowed after order completion / session ends
F14.4 | E14 | Quality & NFR Compliance | Security: OWASP scan, pentest, PCI-DSS checklist | 5.4 | Must | 5 | QA | S16 | F05.7 | No open High/Critical findings remain
F14.5 | E14 | Quality & NFR Compliance | DR drill: backup/restore, RTO 4h / RPO 15 min | 5.7 | Must | 3 | QA | S16 | F01.6 | Successful restore with evidence
|  |  | TOTAL RELEASE 1 SCOPE |  |  | 653

## 3. Epic Summary
SUMMARY BY EPIC
Epic | Epic Name | Service / Domain | Track | Features | Estimate (dev-day) | % of total scope | Start sprint | End sprint
E01 | Platform Foundation | Cross-cutting | A | 11 | 86 | 13.17% | S0 | S3
E02 | User Service - Identity & Access | User Service | A | 6 | 39 | 5.972% | S3 | S5
E03 | Notification Service | Notification Service | B | 4 | 22 | 3.369% | S3 | S4
E04 | Catalog Service | Catalog Service | A | 5 | 30 | 4.594% | S5 | S7
E05 | Commerce - Cart, Checkout, Payment | Commerce Service | A | 7 | 73 | 11.18% | S7 | S11
E06 | Commerce - Order Management | Commerce Service | A | 6 | 49 | 7.504% | S11 | S15
E07 | Auction - Session Management | Auction Service | B | 5 | 34 | 5.207% | S6 | S9
E08 | Auction - Bidding | Auction Service | B | 6 | 48 | 7.351% | S9 | S12
E09 | Auction - Settlement | Auction Service | B | 5 | 36 | 5.513% | S12 | S14
E10 | Fulfillment - Inventory / Warehouse | Fulfillment Service | B | 6 | 42 | 6.432% | S4 | S15
E11 | Fulfillment - Shipping & Logistics | Fulfillment Service | A | 5 | 26 | 3.982% | S14 | S16
E12 | User Reputation | User Service | A | 3 | 14 | 2.144% | S13 | S16
E13 | Web Frontend (Buyer / Seller / Admin) | Frontend | FE | 9 | 101 | 15.47% | S2 | S15
E14 | Quality & NFR Compliance | Cross-cutting | QA | 6 | 53 | 8.116% | S3 | S16
| TOTAL |  |  | 84 | 653

## 4. Sprint Plan
SPRINT PLAN — LOAD VS. CAPACITY BY TRACK
Capacity per sprint at 100%: Track A = 20 · Track B = 16 · Frontend = 8 · QA = 8 dev-day. S8 runs 3 calendar weeks to absorb the 5-day Tet break (06/02/2027); capacity is counted at 80% due to reduced productivity around the break.
Sprint | From | To | Weeks | Capacity | Sprint theme | A load | A cap | B load | B cap | FE load | FE cap | QA load | QA cap | Total load | Total cap | % used
S0 | 28/09/2026 | 09/10/2026 | 2 | 100% | Tech stack training: Backend (Java, Spring Boot) & Frontend (ReactJS, HTML, CSS) | 20 | 20 | 16 | 16 | 8 | 8 | 0 | 8 | 44 | 52 | 84.62%
S1 | 12/10/2026 | 23/10/2026 | 2 | 100% | Inception & platform bootstrap | 16 | 20 | 0 | 16 | 0 | 8 | 0 | 8 | 16 | 52 | 30.77%
S2 | 26/10/2026 | 06/11/2026 | 2 | 100% | Platform: gateway, event bus, environments | 19 | 20 | 0 | 16 | 6 | 8 | 0 | 8 | 25 | 52 | 48.08%
S3 | 09/11/2026 | 20/11/2026 | 2 | 100% | Platform completion + User Service | 17 | 20 | 15 | 16 | 6 | 8 | 5 | 8 | 43 | 52 | 82.69%
S4 | 23/11/2026 | 04/12/2026 | 2 | 100% | Authentication & Event log + Inventory record | 16 | 20 | 15 | 16 | 8 | 8 | 5 | 8 | 44 | 52 | 84.62%
S5 | 07/12/2026 | 18/12/2026 | 2 | 100% | IAM completion + Inventory reservation | 19 | 20 | 16 | 16 | 8 | 8 | 0 | 8 | 43 | 52 | 82.69%
S6 | 04/01/2027 | 15/01/2027 | 2 | 100% | Catalog + Inventory release + Auction session creation | 19 | 20 | 16 | 16 | 6 | 8 | 0 | 8 | 41 | 52 | 78.85%
S7 | 18/01/2027 | 29/01/2027 | 2 | 100% | Catalog search + Auction lifecycle + Shopping cart | 17 | 20 | 16 | 16 | 6 | 8 | 0 | 8 | 39 | 52 | 75%
S8 | 01/02/2027 | 19/02/2027 | 3 | 80% | Tet holiday - reduced capacity: Cart & pricing + Auction cancellation | 16 | 16 | 12 | 12.8 | 6 | 6.4 | 0 | 6.4 | 34 | 41.6 | 81.73%
S9 | 22/02/2027 | 05/03/2027 | 2 | 100% | Checkout + Bidding | 14 | 20 | 12 | 16 | 7 | 8 | 0 | 8 | 33 | 52 | 63.46%
S10 | 08/03/2027 | 19/03/2027 | 2 | 100% | Stripe payment + Bid concurrency handling | 17 | 20 | 16 | 16 | 8 | 8 | 0 | 8 | 41 | 52 | 78.85%
S11 | 22/03/2027 | 02/04/2027 | 2 | 100% | Payment webhook + Bid history & anti-sniping + Performance testing | 19 | 20 | 15 | 16 | 8 | 8 | 4 | 8 | 46 | 52 | 88.46%
S12 | 05/04/2027 | 16/04/2027 | 2 | 100% | Order creation + Auction settlement start | 19 | 20 | 16 | 16 | 8 | 8 | 4 | 8 | 47 | 52 | 90.38%
S13 | 19/04/2027 | 30/04/2027 | 2 | 100% | Order lifecycle + Settlement + Reputation + E2E automation | 18 | 20 | 16 | 16 | 8 | 8 | 6 | 8 | 48 | 52 | 92.31%
S14 | 03/05/2027 | 14/05/2027 | 2 | 100% | Refunds + Shipping + Settlement completion | 18 | 20 | 16 | 16 | 8 | 8 | 6 | 8 | 48 | 52 | 92.31%
S15 | 17/05/2027 | 28/05/2027 | 2 | 100% | GHN shipping + Feature freeze | 18 | 20 | 16 | 16 | 8 | 8 | 0 | 8 | 42 | 52 | 80.77%
S16 | 31/05/2027 | 11/06/2027 | 2 | 100% | Hardening, performance, pentest, UAT, go-live | 11 | 20 | 0 | 16 | 0 | 8 | 8 | 8 | 19 | 52 | 36.54%
[5 empty] | TOTAL | 293 | 336 | 213 | 268.8 | 109 | 134.4 | 38 | 134.4 | 653 | 873.6 | 74.75%
NOTE: the “Total cap” column includes S16 (the hardening sprint) and all of QA's capacity. The real buffer must be calculated over each track's DELIVERY sprints only — see the table below.
ACTUAL BUFFER BY TRACK (delivery sprints only, EXCLUDING the S16 hardening sprint)
Track | Track name | Delivery sprints | Scope (dev-day) | Capacity (dev-day) | Buffer % | Assessment
A | Track A - Commerce & Platform (Tech Lead 50% + 2 BE) | S1 – S15 | 262 | 296 | 11.49% | Tight — needs scope discipline
B | Track B - Async & Auction (2 BE) | S3 – S15 | 197 | 204.8 | 3.809% | HIGH RISK — add 1 dev
FE | Frontend (1 FE) | S2 – S15 | 101 | 110.4 | 8.514% | Tight — needs scope discipline
QA | QA Automation (1 QA) | S3 – S16 | 38 | 110.4 | 65.58% | Acceptable
Track B (the entire auction flow) is the constraint that governs the pace of the whole plan. Adding 1 backend dev to Track B would raise the buffer from 3.8% to about 22%.

## 5. Milestones
MILESTONES & ACCEPTANCE CRITERIA
Code | Milestone | Date | Sprint | Conditions to declare MET (exit criteria)
M0 | Platform ready | 20/11/2026 | S3 | CI/CD running; event bus can publish/consume; observability has tracing; can deploy to STAGING
M1 | Identity & Catalog | 29/01/2027 | S7 | Sign up / sign in / password reset; product & category CRUD; search <= 800ms; product browsing UI
M2 | Commerce core runs end-to-end | 16/04/2027 | S12 | Cart → checkout → Stripe → order → stock reservation and deduction, running end-to-end on STAGING
M3 | Auction runs end-to-end | 14/05/2027 | S14 | Session creation → concurrent bidding → anti-sniping → settlement → order created from the auction
M4 | Feature complete / code freeze | 28/05/2027 | S15 | GHN waybill; email notifications; reputation-based blocking; all Must-scope done
M5 | Go-Live | 12/06/2027 | S16 | Performance tests meet SRS section 5.1 SLAs; no open High/Critical findings; DR drill passed; UAT signed off
No milestone is scheduled during S8 (Tet, 06/02/2027) or in any sprint running below 100% capacity.

## 6. Deferred
DEFERRED SCOPE — AND WHY
Every item below is in SRS v1.0 but is NOT part of Release 1. The Product Owner needs to sign off on this list.
Code | Item | SRS ref | Reason deferred | Estimate (dev-day) | Release
D01 | Promotions / discount code engine | Section 1.2 (in scope) but MISSING a spec in section 3 | SRS has no spec yet, so it cannot be reliably estimated | 12 | R1.1
D02 | Warehouse selection + multi-warehouse order splitting | 3.6.1 | SRS sets FEATURE_MULTI_WAREHOUSE_ENABLED = false; MVP uses a single warehouse | 16 | R1.1
D03 | Second carrier (GHTK) + multi-carrier strategy | 3.6.2 | 1 carrier is enough for MVP; the adapter framework is already in place | 20 | R1.1
D04 | Push notification channel | 3.2.3 | R1 uses in-app WebSocket for realtime needs | 8 | R1.1
D05 | SMS notification channel | 3.2.3 | SRS sets SMS_NOTIFICATION_ENABLED = false | 6 | R2
D06 | Migrate to OpenSearch + relevance tuning | 3.3.3 | Postgres FTS is sufficient under 500,000 products | 14 | R1.1
D07 | Product discovery (popularity, ending soon, recommendations) | 3.3.3 | Not part of the core transaction flow | 12 | R1.1
D08 | PDF invoice / receipt generation | 3.4.3 | R1 sends an HTML email receipt | 10 | R1.1
D09 | Dynamic role/privilege CRUD (admin-defined roles) | 3.1.1 | R1 uses the fixed RBAC matrix from section 2.7 | 10 | R1.1
D10 | Full violation-handling & penalty engine | 3.1.2 | R1 only deducts points for late payment + manual admin adjustment | 8 | R1.1
D11 | Dispute handling & review flagging | 3.1.2 | Requires a dispute workflow definition (missing from the SRS) | 10 | R2
D12 | Dedicated console for Support Staff | 2.3 / 2.7 | R1: Support uses the Admin console | 12 | R1.1
D13 | Notification preferences & history UI | 3.2.3 | Transactional notifications are always sent - sufficient for R1 | 10 | R1.1
D14 | Transaction summary + detailed reputation display | 3.1.2 | R1 only shows the score and trust level | 14 | R1.1
D15 | Private / restricted auction sessions + access control | 3.5.1 | R1 only supports public sessions | 10 | R1.1
D16 | Carrier performance tracking | 3.6.2 | Needs historical data - not available in R1 | 8 | R2
D17 | Pick / pack & ship workflow in inventory | 3.6.1 | R1: paid → deduct stock → ship, no separate pick/pack | 8 | R1.1
D18 | Admin inventory adjustment UI | 3.6.1 | R1 uses API calls and scripts | 5 | R1.1
D19 | Mutual TLS between services | 5.4 | SRS says "may be applied"; R1 uses K8s network policy | 8 | R2
D20 | Blue-green deployment | 5.7 | R1 uses rolling updates (still zero downtime) | 6 | R1.1
D21 | Seller mobile app | 1.2 (out of scope for v1.0) | SRS already declares this out of scope for v1.0 | 0 | R2
D22 | In-house logistics system | 1.2 (out of scope for v1.0) | SRS already declares this out of scope for v1.0 | 0 | R2
| TOTAL |  |  | 207

## 7. Risks
RISK REGISTER
Score = Probability x Impact (1-5 scale), sorted descending. Risks scoring 20 or above are reviewed every sprint.
Code | Risk | Category | Probability | Impact | Score | Mitigation | Owner
R01 | Capacity shortfall: R1 scope is 609 dev-day against a 6-month / 8-person target | Schedule | High | High | 25 | Decide on one of three options before 30/09/2026: (A) add 3 backend devs to hold the 16/04/2027 date; (B) keep the 8-person team, go-live 12/06/2027; (C) cut auction to R2, go-live 30/04/2027 | PO/PM + Sponsor
R02 | Only 1 frontend dev for 4 UI surfaces (buyer, seller, admin, realtime bidding) | Schedule | High | High | 20 | Use a ready-made admin template (Ant Design Pro / Refine) for admin and seller; no custom design in R1; add 1 more FE from S7 if FE velocity drops below 80% | Tech Lead
R03 | Bid concurrency handling: 3,000 bids/minute, latency <= 300ms, zero lost bids | Technical | High | High | 20 | Spike Redis + optimistic locking in S6 (before real coding in S10); performance test in S11-S12, NOT waiting until S16; split Auction into its own service from day one | Tech Lead
R04 | 7 microservices with 5 devs is roughly 1 dev/service (an anti-pattern), operational overhead too high | Technical | High | Medium | 15 | ADR-002: modular monolith with bounded contexts + separate schemas + event bus, EXCEPT Auction Service, which is split out (due to the 3,000 bids/minute NFR). Split further only when scaling is truly needed | Tech Lead + PO
R05 | SRS gaps remain: missing System Context / Architecture / Component diagrams; promotions are in scope but unspecified; dispute workflow and Support Staff role are missing | Requirements | High | Medium | 15 | BA completes SRS v1.1 before S4 (04/12/2026); promotions move to R1.1; disputes move to R2. PO signs off on the gap list | PO + BA (HauNK)
R06 | Tet 2027 (06/02) plus Christmas and New Year cost roughly 2.5 weeks of capacity | Calendar | High | Medium | 15 | Already built into the plan: S8 runs 3 weeks at 80% capacity; the 19/12-03/01 break is not counted as a sprint; no milestone is scheduled in S8 | PM
R10 | Key-person dependency: each domain is owned by just 1 dev | People | High | Medium | 15 | Require 2 reviewers per PR; rotate pairing once per sprint; ADRs and OpenAPI stay living documents; no long leave during a milestone sprint | PM + Tech Lead
R11 | Scope creep from mid-cycle stakeholder requests | Schedule | High | Medium | 15 | Change control: every new request must trade 1-for-1 against an existing Must item; only the PO can add work to the sprint backlog | PO
R07 | Strong consistency requirement (orders / payment / auction) on an event-driven architecture | Technical | Medium | High | 12 | ADR-003: Saga + Transactional Outbox + idempotency keys on every critical API; contract tests are mandatory in CI | Tech Lead
R08 | Stripe integration and PCI-DSS compliance | Compliance | Medium | High | 12 | Use Stripe Elements/Checkout so card data never touches our systems; PCI-DSS SAQ-A checklist from S10; pentest in S16 | Tech Lead + QA
R09 | Quality and readiness of the GHN sandbox / carrier API | External | Medium | Medium | 9 | Request sandbox access from S11 (before coding in S15); mock adapter + contract tests to avoid being blocked; fallback is manual waybill creation | Tech Lead
R12 | Unit test coverage >= 70% (NFR 5.6) sacrificed under deadline pressure | Quality | Medium | Medium | 9 | CI coverage gate blocks merges from S3; DoD requires tests; no exceptions - technical debt is tracked as a defect | QA + Tech Lead

## 8. Team & Process
TEAM, CAPACITY & WORKING PROCESS
A. TEAM CONFIGURATION (8 people)
Role | Count | Dev FTE | Assignment | Key responsibilities
Product Owner / Project Manager | 1 | 0 | Both tracks - Tuan | Owns the backlog and its priority order; the ONLY person allowed to add work to the sprint backlog; runs change control; reports to stakeholders; signs off on the deferred list
Tech Lead / Solution Architect | 1 | 0.5 | Track A (plus ADR ownership, reviews both tracks) | Owns ADRs and contracts (OpenAPI + event schema); reviews 100% of PRs on critical flows; runs technical spikes; accountable for meeting the NFRs in SRS section 5
Backend Developer | 4 | 4 | 2 on Track A, 2 on Track B | Writes code with unit and integration tests per the DoD; 2 on Track A (platform and commerce), 2 on Track B (auction and inventory); rotates pairing once per sprint
Frontend Developer | 1 | 1 | Shared | Buyer web, admin and seller portal (using templates), realtime bidding UI; owns the design system and accessibility
QA / Automation Engineer | 1 | 0 | Shared (capacity tracked separately) | Test strategy; automation framework, contract tests and E2E; performance testing; owns the CI quality gate
TOTAL | 8 | 5.5
B. DEFINITION OF READY — not met means it does NOT go into a sprint
• Has a clear problem statement and user value: who, does what, to get what
• Acceptance criteria written as Given-When-Then, and measurable
• API contract (OpenAPI) and event schema agreed with dependent services
• Dependencies identified, and each is either done or has a mock/stub available
• Estimate is no more than 10 dev-day (larger items must be split — a story can't span sprints)
• Has a wireframe if there's a UI change
• Clearly identifies which SRS section 2.6 configuration is affected and what its default value is
C. DEFINITION OF DONE — not met means it does NOT count as finished
• Code merged to main; approved by 2 reviewers (mandatory for critical flows: payment, orders, bidding, settlement)
• Unit test coverage >= 70% for the changed module — a CI quality gate blocks merges (NFR section 5.6)
• Contract tests pass; OpenAPI spec updated and auto-published
• Domain events published to the correct schema and verified in the Event Log Service (SRS section 3.2.1)
• APIs are idempotent for critical operations: order creation, payment callback, bidding, settlement (NFR section 5.3)
• Structured logs carry a trace-id; request rate / error rate / p95, p99 latency metrics are exposed (NFR section 5.5)
• Audit logs fully record important actions, and are immutable (NFR section 5.8)
• Successfully deployed to STAGING; QA has verified on STAGING
• No open Major/Critical defects; relevant performance SLAs from section 5.1 are measured and met
D. CADENCE
Activity | Frequency | Duration | Attendees | Output
Daily standup | Daily, 9:15 | 15 min | Whole team | Blockers are named and someone owns unblocking them that day
Sprint planning | Monday of each sprint | 2 hours | Whole team | Sprint goal and sprint backlog committed
Backlog refinement | Wednesday of week 1 | 90 min | PO, Tech Lead, 1 dev per track, QA | Next sprint's features reach Definition of Ready
Sprint review / demo | Thursday, end of sprint | 60 min | Whole team + stakeholders | Demo on STAGING (never on a dev machine)
Retrospective | Thursday, end of sprint | 60 min | Whole team | At most 2 action items, each with an owner and a deadline
Architecture review | Every 2 sprints | 90 min | Tech Lead + Backend + PO | New ADR or an amendment to an existing one
Risk review | Every sprint | 30 min | PM, Tech Lead, PO | Risk register updated; risks scoring 20+ get a new action
Milestone gate | Per sheet 5 | 2 hours | Whole team + Sponsor | GO / NO-GO decision based on exit criteria
E. METRICS TRACKED EVERY SPRINT
• Velocity (dev-day completed) versus commitment — flag if below 85% for 2 consecutive sprints
• Scope added / removed within a sprint (target is zero — every change must be a 1-for-1 trade-off)
• Defect leakage rate from STAGING to UAT
• Unit test coverage and contract test count (may only increase, never decrease)
• Number of ADRs still “proposed” for more than 1 sprint (architecture debt)
• R1 scope burn-down: dev-day remaining versus sprints remaining